## 00_Dashboard
Backlog de Implementación — PMS Hotel Boutique
Fuente oficial de trabajo para WEB-1..4 y ANDROID-1. Archivo canónico: docs/Backlog_Implementacion_PMS_V1.xlsx. No avanzar una tarea dependiente hasta que sus dependencias estén COMPLETADAS y el DoD haya pasado QA.
Total tareas | READY | En progreso | En QA | Bloqueadas | Completadas
141 | 2 | 0 | 0 | 0 | 0
Owner | Total asignadas | Estado inicial READY |  | Aplicación | Total | Completadas
WEB-1 | 17 | 1 |  | WEB | 114 | 0
WEB-2 | 26 | 0 |  | ANDROID | 27 | 0
WEB-3 | 45 | 0
WEB-4 | 26 | 0
ANDROID-1 | 27 | 1
Flujo obligatorio
PENDIENTE | → | READY | →
EN_PROGRESO | → | EN_QA | → COMPLETADA
Si QA falla | → | EN_PROGRESO | corregir y re-QA
Cómo usar este backlog: 1) Cada integrante filtra Owner y Estado=READY. 2) Verifica dependencias y DoR. 3) Cambia a EN_PROGRESO y registra rama/fecha. 4) Al terminar, abre PR, adjunta evidencia y cambia a EN_QA. 5) El reviewer ejecuta criterios de aceptación + DoD. Si falla, vuelve a EN_PROGRESO. 6) Solo con PASS se marca COMPLETADA. Para tareas shared/cross-domain, el reviewer indicado es obligatorio.

## 01_Backlog
ID | Sprint | App | Área | Owner | Reviewer | Módulo | Tipo | Prioridad | Estado | Dependencias | Figma / Fuente | Node ID | Ruta | Tarea | Pasos obligatorios | Criterios de aceptación | Definition of Ready específica | DoD específico de tarea | Pruebas obligatorias | Archivos / carpetas esperadas | Rama sugerida | PR / Evidencia | Fecha inicio | Fecha fin | Observaciones
IMP-WEB-0001 | S0 Foundation | WEB | Infra | WEB-1 | WEB-2 | foundation | INFRA | CRÍTICA | READY |  | V3 — 00 Foundations & Core ADRs |  | N/A | Inicializar Next.js Web en el monorepo | Crear Next.js App Router + TypeScript dentro de frontend/pms-hotel-web; usar npm; conservar docs/AGENTS; no crear features. | package.json y package-lock.json existen; npm run dev y build funcionan; no pnpm-workspace; no segundo .git; 0 features. | Rama chore/web-sprint-0; docs V2 leídos; Node/npm disponibles. | Build PASS; monorepo intacto; sin features ni módulos de negocio. | npm run build | frontend/pms-hotel-web/{package.json,package-lock.json,next.config.ts,next-env.d.ts} | chore/web-sprint-0
IMP-WEB-0002 | S0 Foundation | WEB | Infra | WEB-1 | WEB-4 | foundation | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0001 | V3 — 00 Foundations & Core ADRs |  | N/A | Configurar TypeScript strict, alias y src/ | Activar strict; @/*->src/*; crear app/modules/shared/data/lib; no crear módulos de negocio vacíos. | npm run typecheck PASS; alias funciona; 5 carpetas base existen; modules no contiene catálogo vacío. | IMP-WEB-0001 COMPLETADA. | Typecheck PASS; 0 any introducido por bootstrap; boundaries base respetados. | npm run typecheck | tsconfig.json; src/{app,modules,shared,data,lib} | chore/web-sprint-0
IMP-WEB-0003 | S0 Foundation | WEB | Routing | WEB-1 | WEB-3 | app-routing | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0002 | Requisito docente: (public)/(private) |  | / y /dashboard | Crear Route Groups y smoke pages | Crear (public)/layout.tsx+page.tsx y (private)/layout.tsx+dashboard/page.tsx; no crear private/page.tsx. | / carga desde public; /dashboard desde private; no colisión; layouts renderizan children; smoke sin UI final. | IMP-WEB-0002 COMPLETADA. | Build PASS; rutas PASS; Route Groups permanecen físicos. | npm run build + smoke manual | src/app/(public)/*; src/app/(private)/* | chore/web-sprint-0
IMP-WEB-0004 | S0 Foundation | WEB | Design System | WEB-2 | WEB-1 | shared/styles | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0001 | frontend/pms-hotel-web/docs/31_DESIGN_TOKEN_FOUNDATION.md |  | N/A | Implementar tokens reales de Figma | Crear tokens.css desde 31_DESIGN_TOKEN_FOUNDATION.md; primitivas, aliases, spacing, radius, typography, shadow; no inventar dark mode. | Todos los tokens documentados están presentes; semantic aliases referencian primitives; Lora/Inter y shadow coinciden; 0 valores inventados. | 31_DESIGN_TOKEN_FOUNDATION.md presente. | Revisión 1:1 contra Figma handoff; build PASS. | build + revisión manual | src/shared/styles/tokens.css | chore/web-sprint-0
IMP-WEB-0005 | S0 Foundation | WEB | Design System | WEB-2 | WEB-1 | shared/styles | INFRA | ALTA | PENDIENTE | IMP-WEB-0003, IMP-WEB-0004 | Typography / Global foundation |  | N/A | Configurar globals.css y tipografías | Importar tokens; reset/base mínimos; cargar Lora/Inter con mecanismo Web aprobado; no versionar fuentes. | Smoke pages usan surface/page y text/primary; fuentes cargan; 0 estilos de feature; no font binaries. | 0003 y 0004 COMPLETADAS. | Build PASS; visual smoke. | npm run build | src/app/globals.css; src/app/layout.tsx | chore/web-sprint-0
IMP-WEB-0006 | S0 Foundation | WEB | Infra | WEB-4 | WEB-1 | lib/http | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0002 | frontend/pms-hotel-web/docs/09_SERVICE_RULES.md |  | N/A | Crear cliente HTTP base con fetch | Crear env tipado y http client; base URL; headers; errores de transporte; no endpoints de dominio; no localStorage. | Cliente fetch reutilizable; URL por env; errores tipados; 0 endpoints business; 0 auth real. | 0002 COMPLETADA. | Tests del cliente base + lint/typecheck. | Vitest + typecheck | src/lib/http/*; src/lib/env.ts | chore/web-sprint-0
IMP-WEB-0007 | S0 Foundation | WEB | Arquitectura | WEB-4 | WEB-3 | lib/errors | INFRA | ALTA | PENDIENTE | IMP-WEB-0002 | frontend/pms-hotel-web/docs/07_MAPPER_RULES.md |  | N/A | Crear DomainMappingError | Error tipado para campo DTO obligatorio inválido; code seguro; no payload/PII; test mínimo. | Error permite code seguro; no serializa DTO crudo; test PASS. | 0002 COMPLETADA. | Vitest/lint/typecheck PASS. | Vitest | src/lib/errors/domain-mapping-error.ts | chore/web-sprint-0
IMP-WEB-0008 | S0 Foundation | WEB | State | WEB-2 | WEB-4 | app/providers | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0002 | frontend/pms-hotel-web/docs/10_HOOK_AND_STATE_RULES.md |  | N/A | Configurar TanStack Query | Instalar @tanstack/react-query; providers.tsx; QueryClientProvider en root; defaults conservadores; sin queries de negocio. | Provider activo; smoke pages renderizan; 0 queries business; sin optimistic defaults sensibles. | 0002 COMPLETADA. | Smoke test provider + build. | Vitest/RTL + build | src/app/providers.tsx; package.json | chore/web-sprint-0
IMP-WEB-0009 | S0 Foundation | WEB | Mocks | WEB-3 | WEB-4 | data/mocks | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0006 | frontend/pms-hotel-web/docs/23_MOCK_API.md |  | N/A | Configurar MSW | Instalar MSW; generar worker; browser/server/handlers; activar con NEXT_PUBLIC_USE_MOCK_API=true; no fixtures business. | MSW intercepta request técnico; flag ON/OFF funciona; UI no importa mocks; worker generado oficialmente. | 0006 COMPLETADA. | Vitest con MSW + build. | Vitest | public/mockServiceWorker.js; src/data/mocks/* | chore/web-sprint-0
IMP-WEB-0010 | S0 Foundation | WEB | Testing | WEB-3 | WEB-2 | test | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0001 | frontend/pms-hotel-web/docs/26_TESTING.md |  | N/A | Configurar Vitest + Testing Library | Instalar Vitest/RTL/jsdom; config/setup; smoke test; no Playwright. | npm test PASS; RTL renderiza smoke; no Playwright/test:e2e. | 0001 COMPLETADA. | npm test PASS. | npm test | vitest.config.ts; src/test/setup.ts | chore/web-sprint-0
IMP-WEB-0011 | S0 Foundation | WEB | Calidad | WEB-4 | WEB-3 | eslint | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0002 | frontend/pms-hotel-web/docs/04_MODULE_BOUNDARIES.md |  | N/A | Configurar ESLint flat + boundaries | Impedir shared->modules, lib->modules y deep imports cross-module; max warnings 0. | npm run lint PASS; regla detecta violación temporal y el repo final queda limpio. | 0002 COMPLETADA. | Lint PASS. | npm run lint | eslint.config.mjs | chore/web-sprint-0
IMP-WEB-0012 | S0 Foundation | WEB | Routing | WEB-1 | WEB-2 | public-layout | INFRA | ALTA | PENDIENTE | IMP-WEB-0003, IMP-WEB-0005 | Public Web Final V3 | 17:2 | / | Crear PublicLayout técnico | Header-area, main y footer-area semánticos; tokens; sin navegación final. | Layout reusable; landmarks correctos; smoke page sin UI final ni controles muertos. | 0003/0005 COMPLETADAS. | Build + revisión DOM. | build + smoke | src/app/(public)/layout.tsx | chore/web-sprint-0
IMP-WEB-0013 | S0 Foundation | WEB | Routing | WEB-3 | WEB-2 | private-layout | INFRA | ALTA | PENDIENTE | IMP-WEB-0003, IMP-WEB-0005 | Private Web implementation source |  | /dashboard | Crear PrivateLayout técnico | Sidebar-area, header-area y main; tokens; sin menú real, roles ni auth. | Shell reusable; /dashboard smoke; 0 navegación cross-role. | 0003/0005 COMPLETADAS. | Build + revisión DOM. | build + smoke | src/app/(private)/layout.tsx | chore/web-sprint-0
IMP-WEB-0014 | S0 Foundation | WEB | CI | WEB-4 | WEB-1 | github-actions | INFRA | CRÍTICA | PENDIENTE | IMP-WEB-0010, IMP-WEB-0011 | Monorepo workflow |  | N/A | Crear CI Web | Crear .github/workflows/web-ci.yml en root; working-directory Web; npm ci, lint, typecheck, test, build. | Workflow válido; no .github dentro de Web; falla si un check falla. | Testing/lint listos. | Ejecución local equivalente PASS. | npm ci + lint + typecheck + test + build | .github/workflows/web-ci.yml | chore/web-sprint-0
IMP-WEB-0015 | S0 Foundation | WEB | Calidad | WEB-4 | WEB-2 | package-scripts | INFRA | ALTA | PENDIENTE | IMP-WEB-0010, IMP-WEB-0011 | Web DoD |  | N/A | Definir scripts npm estándar y check | Agregar dev/build/start/lint/typecheck/test/test:watch/check; check=lint+typecheck+test+build; no e2e. | npm run check PASS; no Playwright. | 0010/0011 COMPLETADAS. | check PASS. | npm run check | package.json | chore/web-sprint-0
IMP-WEB-0016 | S0 Foundation | WEB | Documentación | WEB-2 | WEB-3 | docs | DOC | ALTA | PENDIENTE | IMP-WEB-0001, IMP-WEB-0002, IMP-WEB-0003, IMP-WEB-0004, IMP-WEB-0005, IMP-WEB-0006, IMP-WEB-0007, IMP-WEB-0008, IMP-WEB-0009, IMP-WEB-0010, IMP-WEB-0011, IMP-WEB-0012, IMP-WEB-0013, IMP-WEB-0014, IMP-WEB-0015 | Docs V2 + token foundation |  | N/A | Actualizar ADR y README con configuración real | Verificar y sincronizar la documentación con la implementación real de IMP-WEB-0001 a IMP-WEB-0015. Registrar npm, Next.js/App Router, Route Groups, fetch, TanStack Query, MSW, Vitest/Testing Library, Playwright diferido, boundaries, DomainMappingError, design tokens, DoR de infraestructura y Node IDs solo como trazabilidad. No reescribir documentos no relacionados. | README y ADR/docs describen exactamente lo implementado en 0001-0015; no hay contradicciones; todas las rutas de documentos existen; backlog y documentación usan las mismas decisiones. | Config técnica implementada. | Review documental. | manual review | docs globales/Web afectados | chore/web-sprint-0
IMP-WEB-0017 | S0 Foundation | WEB | QA | WEB-2 | WEB-1 | foundation | QA | CRÍTICA | PENDIENTE | IMP-WEB-0001, IMP-WEB-0002, IMP-WEB-0003, IMP-WEB-0004, IMP-WEB-0005, IMP-WEB-0006, IMP-WEB-0007, IMP-WEB-0008, IMP-WEB-0009, IMP-WEB-0010, IMP-WEB-0011, IMP-WEB-0012, IMP-WEB-0013, IMP-WEB-0014, IMP-WEB-0015, IMP-WEB-0016 | V3 — 00 Foundations & Core ADRs |  | / y /dashboard | Cerrar Sprint 0 Web | Ejecutar check; validar CI, smoke routes, tokens, Query, MSW, boundaries; confirmar 0 modules/features/shared UI especulativos. | npm run check PASS; CI PASS; / y /dashboard PASS; 0 features business; docs sincronizados. | Todas dependencias COMPLETADAS. | Global DoD Web PASS; evidencia adjunta. | npm run check + CI + smoke | todo S0 | chore/web-sprint-0
IMP-WEB-S101 | S1 Public Booking | WEB | Shared | WEB-1 | WEB-2 | shared/components | SHARED | ALTA | PENDIENTE | IMP-WEB-0017 | Public 01 Booking |  | N/A | Crear Button shared por primer uso | Extraer solo variantes usadas; tokens; keyboard/focus; disabled/loading si Figma lo usa. | Booking usa Button sin duplicar estilos; API mínima; a11y PASS. | S0 completo; primer uso identificado. | Tests render/disabled + visual. | Vitest/RTL | src/shared/components/button/* | feature/shared-button
IMP-WEB-S102 | S1 Public Booking | WEB | Shared | WEB-1 | WEB-2 | shared/components | SHARED | ALTA | PENDIENTE | IMP-WEB-0017 | Public 01 Booking |  | N/A | Crear Input shared | Label/help/error/required/disabled/focus; no validación business interna. | Formulario booking no duplica Input; errores accesibles. | S0 completo. | RTL + visual. | Vitest/RTL | src/shared/components/input/* | feature/shared-input
IMP-WEB-0101 | S1 Public Booking | WEB | Público | WEB-1 | WEB-4 | booking | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S101, IMP-WEB-S102 | Public 01 Booking | 17:2 | / | Implementar búsqueda pública | Fechas, ocupación, habitaciones; validación de forma; submit vía hook/service; no fetch UI. | Rango/ocupación válidos; errores accesibles; submit no fetch directo; criterios preservados. | DTO search provisional + API availability acordada. | Global DoD; mapper/service/hook si hay red. | Vitest/RTL + visual | src/modules/booking/*; public page | feature/booking-search
IMP-WEB-0102 | S1 Public Booking | WEB | Público | WEB-4 | WEB-1 | availability | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0101 | Public 01 Booking + Availability |  | /habitaciones | Crear contrato/service/mapper de disponibilidad | DTO provisional; service fetch; mapper AvailabilityOption; MSW success/empty/error/delay. | Service retorna DTO; Domain limpio con ATS/amount/currency; invalid required -> DomainMappingError. | Search criteria definidos. | Mapper/service tests. | Vitest | src/modules/availability/*; mocks | feature/availability-public-contract
IMP-WEB-0103 | S1 Public Booking | WEB | Público | WEB-1 | WEB-4 | booking | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0102 | Public 01 Booking |  | /habitaciones | Implementar resultados de disponibilidad | Cards de room types; loading/error/empty; precio/condiciones; selection a detalle. | 0 DTO UI; ATS 0 no se presenta disponible; selección conserva búsqueda; states completos. | 0102 COMPLETADA. | RTL states + visual. | Vitest/RTL | route /habitaciones; booking components | feature/availability-results
IMP-WEB-0104 | S1 Public Booking | WEB | Público | WEB-1 | WEB-4 | rooms | FEATURE | ALTA | PENDIENTE | IMP-WEB-0103 | Public 01 Booking |  | /habitaciones/[roomTypeId] | Implementar detalle de RoomType | Galería/datos/amenities/policy/precio; CTA selección; no Room físico. | Route usa roomTypeId; no expone roomId; CTA preserva búsqueda. | RoomType contract listo. | RTL + visual. | Vitest/RTL | src/modules/rooms/*; route detail | feature/public-room-detail
IMP-WEB-0105 | S1 Public Booking | WEB | Público | WEB-1 | WEB-4 | booking | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0104 | Public 03 Multi-room |  | /reserva | Implementar carrito multi-room | N selections como futuras ReservationStay; add/remove/edit; totals. | Una Reservation draft con N stays; no una Reservation por habitación; total correcto. | BookingDraft Domain listo. | Unit totals + RTL. | Vitest/RTL | booking cart/model | feature/multi-room-cart
IMP-WEB-0106 | S1 Public Booking | WEB | Público | WEB-1 | WEB-3 | booking | FEATURE | ALTA | PENDIENTE | IMP-WEB-0105 | Public 03 Multi-room |  | /reserva | Implementar ocupantes por Stay | Asignar occupants por stay; booking guest distinto; validar capacity recibida. | Occupants no se copian obligatoriamente; capacity violation visible. | StaySelection constraints listas. | Unit/RTL. | Vitest/RTL | booking occupants components | feature/multi-room-occupants
IMP-WEB-0107 | S1 Public Booking | WEB | Público | WEB-1 | WEB-2 | checkout | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0106 | Public 04 Checkout |  | /reserva/checkout | Implementar datos del booking guest | Guest checkout; formulario identidad/contacto; login opcional; no crear account automáticamente. | Puede continuar sin cuenta; GuestInput Domain; Staff separado. | Create booking contract provisional. | RTL form+a11y. | Vitest/RTL | src/modules/checkout/* | feature/guest-checkout-data
IMP-WEB-0108 | S1 Public Booking | WEB | Público | WEB-2 | WEB-1 | auth | FEATURE | ALTA | PENDIENTE | IMP-WEB-0107 | Public 02 Identidad |  | /acceso | Implementar acceso opcional email/Google | Continuar invitado, email y Google; preservar draft; sin auth real persistente si backend no existe. | Google/email opcionales; no localStorage token; retorno preserva booking. | Auth mock contract listo. | RTL branches. | Vitest/RTL | src/modules/auth/*; /acceso | feature/guest-auth-optional
IMP-WEB-0109 | S1 Public Booking | WEB | Público | WEB-4 | WEB-1 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0107 | Public 04 Checkout |  | /reserva/checkout | Crear garantía/pago provisional | Payment/Guarantee DTO, mapper, service; token/provider refs; no PAN/CVV. | DTO/Domain sin PAN/CVV; success/failure mock; no secrets. | Checkout data listo. | Mapper/service + security review. | Vitest | src/modules/payments/*; mocks | feature/booking-payment-contract
IMP-WEB-0110 | S1 Public Booking | WEB | Público | WEB-1 | WEB-4 | checkout | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0109, IMP-WEB-0106 | Public 04 Checkout |  | /reserva/checkout | Integrar review final y revalidación | Resumen stays/price/policy/payment; revalidate availability/rate antes submit; anti-double-submit. | No éxito si revalidación falla; submitting deshabilita; resumen coincide draft. | Availability/payment contracts listos. | Hook integration success/conflict. | Vitest/RTL | checkout review | feature/booking-final-review
IMP-WEB-0111 | S1 Public Booking | WEB | Público | WEB-3 | WEB-1 | reservations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0110 | Reservation Engine + confirmation |  | /reserva/confirmacion | Crear contract de Reservation multi-room | Request una Reservation con stays[]; response Reservation + stay IDs; bookingGuest separado. | Mapper conserva stays; no flatten; MSW devuelve business IDs. | Final review listo. | Mapper/service. | Vitest | src/modules/reservations/*; mocks | feature/create-reservation-contract
IMP-WEB-0112 | S1 Public Booking | WEB | Público | WEB-1 | WEB-3 | checkout | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0111 | Public 04 Confirmation |  | /reserva/confirmacion | Implementar confirmación | Mostrar reservation id, stays, fechas, total/status; CTA cuenta/continuar; solo tras success. | IDs business; multi-room completo; error no navega a éxito. | 0111 COMPLETADA. | RTL success/failure+visual. | Vitest/RTL | confirmation route/components | feature/booking-confirmation
IMP-WEB-0113 | S1 Public Booking | WEB | QA | WEB-1 | WEB-4 | booking | QA | CRÍTICA | PENDIENTE | IMP-WEB-0101, IMP-WEB-0103, IMP-WEB-0104, IMP-WEB-0105, IMP-WEB-0106, IMP-WEB-0107, IMP-WEB-0110, IMP-WEB-0112 | Public 01/03/04 | 17:2 | / -> /reserva/confirmacion | QA journey Booking público | Guest single/multi-room; optional auth; loading/error/empty; revalidation; Figma parity. | 0 rutas/control muertos; no login obligatorio; no DTO UI; no PAN/CVV; responsive básico. | Tareas journey completas. | Global DoD + regression. | npm run check + manual journey | Public Booking | test/public-booking-regression
IMP-WEB-0201 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-1 | auth | FEATURE | ALTA | PENDIENTE | IMP-WEB-0017 | Public 02 Identidad y cuenta |  | /acceso | Crear GuestAccount/ExternalIdentity contracts | DTO/mapper/service de GuestAccount separado de GuestProfile; Google ExternalIdentity opcional; sin Staff. | Account/Profile separados; mapper tests; UI futura no recibe provider JSON. | S0 completo; auth docs revisadas. | Mapper/service PASS; no localStorage token. | Vitest | src/modules/auth/* | feature/guest-account-contract
IMP-WEB-0202 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-1 | auth | FEATURE | ALTA | PENDIENTE | IMP-WEB-0201 | Public 02 Identidad y cuenta |  | /acceso | Implementar acceso Guest final | Email + Google optional + continuar invitado; loading/error; retorno a booking/account. | Google no obligatorio; Guest/Staff separados; errores recuperables; Figma parity. | 0201 COMPLETADA. | RTL+a11y+visual. | Vitest/RTL | /acceso; auth components | feature/guest-access
IMP-WEB-0203 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-3 | account | FEATURE | ALTA | PENDIENTE | IMP-WEB-0201 | Public 05 Cuenta |  | /cuenta | Crear Account/Profile contracts y dashboard | Service/mapper de account/profile; dashboard summary; loading/error. | Account y Profile no se fusionan; no PII logs; Domain-only UI. | Contracts listos. | Mapper/service + RTL states. | Vitest/RTL | src/modules/account; profile; /cuenta | feature/account-dashboard
IMP-WEB-0204 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-3 | profile | FEATURE | ALTA | PENDIENTE | IMP-WEB-0203 | Public 05 Perfil |  | /cuenta/perfil | Implementar edición de perfil | Formulario Domain; submit service; submitting/error; no tocar auth fields no relacionados. | Perfil se guarda mock; GuestAccount permanece intacto; a11y form. | Update contract listo. | RTL validation/save. | Vitest/RTL | profile route/components | feature/guest-profile
IMP-WEB-0205 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-3 | account/reservations | FEATURE | ALTA | PENDIENTE | IMP-WEB-0203, IMP-WEB-0111 | Public 05 Historial |  | /cuenta/reservas | Implementar historial de reservas | Consumir Reservation API pública; lista vinculada; empty/error; status. | No deep import; cancelled/no-show visibles; solo datos del Guest. | Reservation public API lista. | RTL list/empty/error + boundary lint. | Vitest/RTL | account reservation history | feature/account-reservations
IMP-WEB-0206 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-3 | account/reservations | FEATURE | MEDIA | PENDIENTE | IMP-WEB-0205 | Public 05 Historial |  | /cuenta/reservas/[reservationId] | Implementar detalle de reserva en cuenta | Mostrar stays, occupants, status/policies; acciones solo Guest; 404/error. | 0 controles Staff; multi-room correcto; route valida business ID. | 0205 COMPLETADA. | RTL detail + security review. | Vitest/RTL | account reservation detail | feature/account-reservation-detail
IMP-WEB-0207 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-4 | rewards | FEATURE | ALTA | PENDIENTE | IMP-WEB-0203 | Public 05 Rewards |  | /cuenta/rewards | Implementar RewardLedger | EARN/REDEEM/EXPIRE/REVERSE; balance + movements; empty/error. | CANCELLED/NO_SHOW no elegibles; ledger append-only; no edit UI. | Reward contract provisional. | Mapper ledger + RTL. | Vitest/RTL | src/modules/rewards/* | feature/rewards
IMP-WEB-0208 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-4 | promotions | FEATURE | ALTA | PENDIENTE | IMP-WEB-0203 | Public 05 Promociones |  | /cuenta/promociones | Implementar Promotions | Eligibility/vigencia/stacking result/reason; empty/error. | Incompatible promo no se muestra combinable; reason visible cuando Domain lo entrega. | Promotion contract listo. | Mapper + RTL. | Vitest/RTL | src/modules/promotions/* | feature/promotions
IMP-WEB-0209 | S2 Identity & Account | WEB | Público | WEB-2 | WEB-4 | invoices | FEATURE | MEDIA | PENDIENTE | IMP-WEB-0203 | Public 05 Facturas |  | /cuenta/facturas | Implementar facturas/documentos | Lista ref/status/date/total; descarga solo URL/ref permitida; empty/error. | No persistir archivo sensible innecesariamente; datos del Guest actual. | Fiscal read contract provisional. | RTL + security. | Vitest/RTL | account invoices | feature/account-invoices
IMP-WEB-0210 | S2 Identity & Account | WEB | QA | WEB-2 | WEB-3 | account | QA | CRÍTICA | PENDIENTE | IMP-WEB-0202, IMP-WEB-0204, IMP-WEB-0206, IMP-WEB-0207, IMP-WEB-0208, IMP-WEB-0209 | Public 02 + 05 |  | /acceso /cuenta/* | QA Identity/Account | Acceso, profile, history, rewards, promos, invoices; auth a11y; Guest/Staff separation. | 0 mezcla Guest/Staff; Google optional; states completos; routes PASS; no PII logs. | S2 tasks completadas. | Global DoD + auth accessibility. | npm run check + manual | S2 | test/account-regression
IMP-WEB-S301 | S3 Reservation Engine | WEB | Shared | WEB-3 | WEB-4 | shared/components | SHARED | ALTA | PENDIENTE | IMP-WEB-0017 | V3 — 01 Reservation Engine |  | N/A | Crear DataTable shared | Header/rows/empty/loading; accesible; API genérica; no reservation logic. | Reservation Center la usa sin columns hardcoded; keyboard/focus razonable. | Primer uso definido. | RTL. | Vitest/RTL | src/shared/components/data-table/* | feature/shared-data-table
IMP-WEB-S302 | S3 Reservation Engine | WEB | Shared | WEB-3 | WEB-2 | shared/components | SHARED | ALTA | PENDIENTE | IMP-WEB-0017 | Reservation Detail |  | N/A | Crear Modal/ConfirmDialog shared | Focus trap/return focus; title/body/actions; destructive variant solo usada. | Cancel/no-show lo reutilizan; ESC/backdrop policy; a11y PASS. | Primer flujo destructive identificado. | RTL focus/escape. | Vitest/RTL | shared modal/confirm-dialog | feature/shared-confirm-dialog
IMP-WEB-0301 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | reservations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301 | V3 — 01 Reservation Engine |  | /reservas | Implementar Reservation Center | List DTO->Domain; filtros/búsqueda; DataTable; loading/error/empty; property scope. | Reservation y stay summary coherentes; no datos property no autorizada; 0 fetch UI. | List contract provisional; property scope mock listo. | Mapper/service/RTL + visual. | Vitest/RTL | src/modules/reservations/*; /reservas | feature/reservation-center
IMP-WEB-0302 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | reservations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0301 | Reservation Detail |  | /reservas/[reservationId] | Implementar detalle de Reservation | Booking guest, stays, occupants, status, source y refs financieras resumidas. | Reservation vs Stay distinguibles; multi-room correcto; Folio vía API pública. | Detail contract listo. | RTL multi-room + visual. | Vitest/RTL | reservation detail route | feature/reservation-detail
IMP-WEB-0303 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | reservations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0302, IMP-WEB-S302 | Cancellation flow |  | /reservas/[reservationId] | Implementar cancelación | Policy preview; penalty/refund/release; confirm; submit; refresh related queries. | No cancel sin preview válido; error preserva original; no double submit. | Cancel preview/apply contract listo. | Integration success/fail. | Vitest/RTL | reservation cancellation | feature/reservation-cancel
IMP-WEB-0304 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | reservations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0302, IMP-WEB-S302 | No-show flow |  | /reservas/[reservationId] | Implementar no-show | Preview cutoff/policy/cargo; confirm; NO_SHOW solo tras success; refresh. | UI no inventa charge; error no cambia status; inventory/folio se refrescan. | No-show contract listo. | Integration. | Vitest/RTL | reservation no-show | feature/reservation-no-show
IMP-WEB-0305 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | reservations | FEATURE | ALTA | PENDIENTE | IMP-WEB-0301 | Waitlist |  | /reservas | Implementar Waitlist y conversión | List entries; revalidate availability/rate; create Reservation; mark converted. | Si revalidation falla no crea success; entry no queda OPEN tras success. | Waitlist contract listo. | Success/conflict integration. | Vitest/RTL | waitlist files | feature/waitlist
IMP-WEB-0306 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | stays | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0302 | Room Move |  | /reservas/[reservationId] | Implementar cambio de habitación | Select Stay/candidate; preview/apply; refresh HK; Folio intacto. | Stay ID conserva; solo room assignment cambia; no cargos duplicados. | Room move contracts listos. | Success/fail integration. | Vitest/RTL | src/modules/stays/room-move* | feature/room-move
IMP-WEB-0307 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | stays | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0302 | Stay Extension |  | /reservas/[reservationId] | Implementar extensión | Nueva departure; preview availability/rate; delta; apply; refresh calendar/inventory/folio. | No apply si gates fallan; departure cambia solo tras success. | Extension contracts listos. | Success/conflict integration. | Vitest/RTL | stay extension files | feature/stay-extension
IMP-WEB-0308 | S3 Reservation Engine | WEB | Privado | WEB-3 | WEB-4 | calendar | FEATURE | ALTA | PENDIENTE | IMP-WEB-0301 | Calendar |  | /calendario | Implementar Calendar/Gantt | Stays por room/date; property scope; select a detail; filters/date nav. | Multi-room representado por stays; no overlap visual; no V1 routes. | Calendar contract listo. | RTL interactions + visual. | Vitest/RTL | calendar route/components | feature/reservation-calendar
IMP-WEB-0309 | S3 Reservation Engine | WEB | QA | WEB-3 | WEB-4 | reservations | QA | CRÍTICA | PENDIENTE | IMP-WEB-0303, IMP-WEB-0304, IMP-WEB-0305, IMP-WEB-0306, IMP-WEB-0307, IMP-WEB-0308 | V3 — 01 Reservation Engine |  | /reservas* | QA Reservation Engine | Cancel/no-show/waitlist/room move/extension/calendar; property scope; multi-room. | 0 Reservation=Stay; financial refs coherentes; 0 dead controls; routes/sidebar PASS. | S3 core completo. | Global DoD + regression. | npm run check + manual | S3 | test/reservation-engine-regression
IMP-WEB-S401 | S4 Folio & Payments | WEB | Shared | WEB-4 | WEB-3 | shared/components | SHARED | ALTA | PENDIENTE | IMP-WEB-0017 | Advanced Folio |  | N/A | Crear StatusBadge shared | Solo statuses usados; semantic tokens; mapping fuera del component. | Reusable Folio/Payment/Reservation; no hardcoded business mapping. | Primer usage definido. | RTL+visual. | Vitest/RTL | shared status-badge | feature/shared-status-badge
IMP-WEB-0401 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | folio | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301, IMP-WEB-S401 | Advanced Folio |  | /folios/[folioId] | Implementar Folio avanzado | Charges/payments/balance/routing/status; loading/error; history read-only salvo acciones. | Balance coherente; Guest/Company/Master distinguibles; no hard delete. | Folio contract provisional. | Mapper/service + RTL rows. | Vitest/RTL | src/modules/folio/* | feature/folio-detail
IMP-WEB-0402 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | folio | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0401, IMP-WEB-S302 | Folio routing/split |  | /folios/[folioId] | Implementar routing y split | Select charges; preview target; apply; conservar amount/history. | Split totals conservan original; no charge duplication; audit/ref visible si existe. | Routing/split contract listo. | Unit conservation + integration. | Vitest/RTL | folio routing/split | feature/folio-routing
IMP-WEB-0403 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | folio | FEATURE | ALTA | PENDIENTE | IMP-WEB-0401 | Folio transfer |  | /folios/[folioId] | Implementar transferencia entre folios | Preview origin/target; validate policy/property; apply compensatory/traced. | Totals preserved; invalid target blocked; no history deletion. | Transfer contract listo. | Integration. | Vitest/RTL | folio transfer | feature/folio-transfer
IMP-WEB-0404 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S401 | Payments lifecycle |  | /pagos | Implementar listado y Domain Payment | DTO->Domain id/amount/currency/status/providerRef/last4; no PAN/CVV. | 0 raw provider payload/secrets; statuses normalizados; states complete. | Payment contract provisional. | Mapper/service + RTL. | Vitest/RTL | src/modules/payments/* | feature/payments-list
IMP-WEB-0405 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0404 | Authorization |  | /pagos | Implementar autorización | Token/provider ref mock; submitting; success AUTHORIZED; failure. | No PAN/CVV persisted; status solo tras response. | Authorization contract listo. | Success/fail/security. | Vitest/RTL | payment authorization | feature/payment-authorization
IMP-WEB-0406 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0405 | Capture |  | /pagos | Implementar capture total/parcial | Parent auth; amount <= authorized remaining; response refs. | No over-capture; parent ref preservada; no optimistic success. | Capture contract listo. | Unit limits + integration. | Vitest/RTL | payment capture | feature/payment-capture
IMP-WEB-0407 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0405 | Void |  | /pagos | Implementar void | Elegibilidad; confirm; apply; refresh status/ref. | Solo elegible; failure no altera status; audit/ref. | Void contract listo. | Integration. | Vitest/RTL | payment void | feature/payment-void
IMP-WEB-0408 | S4 Folio & Payments | WEB | Privado | WEB-4 | WEB-3 | payments | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0406 | Refund |  | /pagos | Implementar refund total/parcial | Max captured-refundable; parent capture ref; reason; multiple refunds. | Suma refunds <= captured; remaining correcto; no negative. | Refund contract listo. | Unit arithmetic + integration. | Vitest/RTL | payment refund | feature/payment-refund
IMP-WEB-0409 | S4 Folio & Payments | WEB | QA | WEB-4 | WEB-3 | finance | QA | CRÍTICA | PENDIENTE | IMP-WEB-0402, IMP-WEB-0403, IMP-WEB-0405, IMP-WEB-0406, IMP-WEB-0407, IMP-WEB-0408 | V3 — 02 Folio & Payments |  | /folios* /pagos | QA Folio/Payments | Balance conservation; routing/split/transfer; auth/capture/void/refund; security. | 0 hard delete; arithmetic PASS; 0 PAN/CVV; routes/roles PASS. | S4 core completo. | Global DoD + security regression. | npm run check + journeys | S4 | test/finance-regression
IMP-WEB-0501 | S5 Operations | WEB | Privado | WEB-3 | WEB-4 | housekeeping | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301, IMP-WEB-S401 | Housekeeping |  | /housekeeping | Implementar Housekeeping base | DTO->Domain DIRTY/CLEAN/INSPECTED; filtros; property scope; loading/error/empty. | Overlays no se mezclan con cleaning status; room IDs coherentes; 0 fetch UI. | HK contract provisional. | Mapper + RTL + visual. | Vitest/RTL | src/modules/housekeeping/* | feature/housekeeping-board
IMP-WEB-0502 | S5 Operations | WEB | Privado | WEB-3 | WEB-2 | housekeeping | FEATURE | ALTA | PENDIENTE | IMP-WEB-0501 | Housekeeping overlays |  | /housekeeping | Implementar DND/Turndown/Pickup | Render overlays separados; DND gate; Turndown window; Pickup; cleaning status unchanged. | Overlay no sustituye DIRTY/CLEAN/INSPECTED; combinaciones coherentes. | Overlay contract listo. | Mapper + RTL combinations. | Vitest/RTL | housekeeping overlays | feature/housekeeping-overlays
IMP-WEB-0503 | S5 Operations | WEB | Privado | WEB-3 | WEB-2 | housekeeping | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0501, IMP-WEB-S302 | Inspection rejected |  | /housekeeping | Implementar rechazo de inspección | Supervisor selecciona room; reason obligatorio; submit devuelve a limpieza; audit/ref. | No INSPECTED tras rechazo; reason requerido; success refresca status. | Contract listo. | Success/no-reason/fail. | Vitest/RTL | housekeeping inspection | feature/inspection-rejected
IMP-WEB-0504 | S5 Operations | WEB | Privado | WEB-3 | WEB-2 | housekeeping | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0501 | Room Discrepancies |  | /housekeeping/discrepancias | Implementar Sleeper/Skipper | Comparar FO vs HK; resolver con reason; before/after; audit. | FO/HK separados; no borrar history; reason obligatorio; RESOLVED solo tras success. | Contract listo. | Mapper + resolution integration. | Vitest/RTL | discrepancies route | feature/room-discrepancies
IMP-WEB-0505 | S5 Operations | WEB | Privado | WEB-3 | WEB-4 | maintenance | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301 | Maintenance |  | /mantenimiento | Implementar órdenes de mantenimiento | OT room/asset/status/reason/dates; list/detail; property scope. | OT no vuelve vendible Room por sí sola; history visible; states complete. | Maintenance contract provisional. | Mapper/service + RTL. | Vitest/RTL | src/modules/maintenance/* | feature/maintenance
IMP-WEB-0506 | S5 Operations | WEB | Privado | WEB-3 | WEB-4 | maintenance | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0505 | OOO vs OOS |  | /mantenimiento | Implementar OOO/OOS diferenciados | Type/dates/reason/impact; create/update via service; no delete Room. | OOO y OOS distintos; ambos preservan dates/reason; availability refresh. | OOO/OOS contract listo. | Status mapping + integration. | Vitest/RTL | maintenance room status | feature/ooo-oos
IMP-WEB-0507 | S5 Operations | WEB | Privado | WEB-3 | WEB-4 | maintenance/housekeeping | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0506, IMP-WEB-0501 | Maintenance release / HK readiness |  | /mantenimiento | Implementar gate de readiness | Resolver OT; si HK pendiente mostrar not sellable; release solo gates PASS. | Resolve OT != sellable; availability cambia solo tras readiness/release. | Contracts Maintenance/HK/Availability listos. | Integration gate cases. | Vitest/RTL | maintenance readiness | feature/maintenance-readiness
IMP-WEB-0508 | S5 Operations | WEB | Privado | WEB-3 | WEB-2 | concierge | FEATURE | MEDIA | PENDIENTE | IMP-WEB-0017 | Operations — Conserjería |  | /conserjeria | Implementar cola interna Conserjería | Tasks internas; guest/reservation refs; status; handoff a Recepción para comunicación. | No direct external message from Conserjería; property scope; states complete. | Concierge contract provisional. | RTL + role review. | Vitest/RTL | src/modules/concierge/* | feature/concierge
IMP-WEB-0509 | S5 Operations | WEB | QA | WEB-3 | WEB-4 | operations | QA | CRÍTICA | PENDIENTE | IMP-WEB-0502, IMP-WEB-0503, IMP-WEB-0504, IMP-WEB-0506, IMP-WEB-0507, IMP-WEB-0508 | V3 — 03 Operations |  | /housekeeping /mantenimiento /conserjeria | QA Operations | Cleaning lifecycle, overlays, inspection, discrepancy, maintenance, OOO/OOS, readiness, messaging boundary. | 0 overlay-as-status; 0 auto-sellable; reasons/audit; role/sidebar PASS. | S5 core completo. | Global DoD + ops regression. | npm run check + manual | S5 | test/operations-regression
IMP-WEB-0601 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-1 | availability | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301 | V3 — 04 Commercial / Availability / Revenue |  | /availability | Implementar matriz ATS | Daily roomType/property/date; sold/OOO/OOS/ATS; filters; no Room delete. | ATS coherente; no contar Reservation incorrectamente; property scope. | Availability contract confirmado. | Math mapper + RTL. | Vitest/RTL | availability private | feature/availability-matrix
IMP-WEB-0602 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-1 | rates | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017 | Rates |  | /revenue/rates | Implementar RatePlan list/detail | RatePlan Domain; rules/status/property; no inventory ownership. | RatePlan no contiene physical inventory; states/filters correctos. | Rate contract provisional. | Mapper + RTL. | Vitest/RTL | src/modules/rates/* | feature/rate-plans
IMP-WEB-0603 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-3 | rates | FEATURE | ALTA | PENDIENTE | IMP-WEB-0602 | Restrictions |  | /revenue/restrictions | Implementar CTA/CTD/MinLOS/Stop Sell | Grid/date controls; preview/apply; no optimistic commit. | Restriction scope correcto; failure no altera success UI. | Restriction contract listo. | Service/mapper + RTL edit. | Vitest/RTL | rate restrictions | feature/restrictions
IMP-WEB-0604 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-3 | inventory | FEATURE | ALTA | PENDIENTE | IMP-WEB-0601 | Sell limits / overbooking |  | /availability | Implementar sell limits/overbooking | Base capacity, adjustment/limit, resulting ATS; edit by permission. | Physical Room count unchanged; ATS recalculated. | Inventory adjustment contract listo. | Calculation tests + RTL. | Vitest/RTL | src/modules/inventory/* | feature/sell-limits
IMP-WEB-0605 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-3 | revenue | FEATURE | ALTA | PENDIENTE | IMP-WEB-0601, IMP-WEB-0602 | Revenue dashboard |  | /revenue | Implementar Revenue KPIs | Occupancy/ADR/RevPAR/pickup/pace; property/date filters; loading/error. | Currency/date scope clear; aggregate after per-property calc. | Revenue read model listo. | Mapper fixtures + RTL. | Vitest/RTL | src/modules/revenue/* | feature/revenue-dashboard
IMP-WEB-0606 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-3 | revenue | FEATURE | ALTA | PENDIENTE | IMP-WEB-0605 | Pickup/Pace/Forecast |  | /revenue | Implementar tendencias Revenue | Pickup/pace/forecast series; actual vs forecast distinguibles; filters. | Group pickup no se confunde con property pickup; forecast no mostrado como actual. | Contracts listos. | Mapper + visual. | Vitest/RTL | revenue trends | feature/revenue-trends
IMP-WEB-0607 | S6 Commercial & Revenue | WEB | Privado | WEB-4 | WEB-3 | channels | FEATURE | MEDIA | PENDIENTE | IMP-WEB-0605 | Channel mix |  | /revenue/channels | Implementar Channel Mix | Distribución por source/channel; totals/percentages; property/date filters. | Totales=100% cuando aplica; unknown no se fusiona silenciosamente. | Channel contract listo. | Totals + RTL. | Vitest/RTL | src/modules/channels/* | feature/channel-mix
IMP-WEB-0608 | S6 Commercial & Revenue | WEB | QA | WEB-4 | WEB-1 | commercial | QA | CRÍTICA | PENDIENTE | IMP-WEB-0601, IMP-WEB-0603, IMP-WEB-0604, IMP-WEB-0605, IMP-WEB-0606, IMP-WEB-0607 | V3 — 04 Commercial / Availability / Revenue |  | /availability /revenue* | QA Commercial/Revenue | ATS/rate separation/restrictions/sell limits/metrics/property scope. | 0 physical inventory mutation; metrics coherent; public availability compatible. | S6 core completo. | Global DoD + calc tests. | npm run check + regression | S6 | test/commercial-regression
IMP-WEB-0701 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | companies | FEATURE | ALTA | PENDIENTE | IMP-WEB-0017, IMP-WEB-S301 | V3 — 05 B2B / Groups |  | /empresas | Implementar Company list/detail | Company Domain; agreements/credit/direct bill summary; property scope. | Company != Guest/Payer; direct bill no auto-approved; states complete. | Company contract provisional. | Mapper/service + RTL. | Vitest/RTL | src/modules/companies/* | feature/companies
IMP-WEB-0702 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | companies/rates | FEATURE | ALTA | PENDIENTE | IMP-WEB-0701, IMP-WEB-0602 | Negotiated rates |  | /empresas/[companyId] | Implementar negotiated rates | Rates por Company+Property+vigencia; link RatePlan. | Rate solo en property acordada; expired/inactive visible; no inventory ownership. | Company+Rate APIs listos. | RTL + mapper. | Vitest/RTL | company negotiated rates | feature/company-negotiated-rates
IMP-WEB-0703 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | agencies | FEATURE | ALTA | PENDIENTE | IMP-WEB-0017 | Agency / B2B |  | /agencias | Implementar Agency list/detail | Agency Domain; contract/commission refs; voucher refs; property scope. | Agency != Company; refs preserved; states complete. | Agency contract provisional. | Mapper + RTL. | Vitest/RTL | src/modules/agencies/* | feature/agencies
IMP-WEB-0704 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | agencies | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0703 | Agency Commission ADR |  | /agencias/[agencyId] | Implementar comisión separada | PERCENT/FIXED; base; payable; guest price unchanged. | Ejemplo Q2000 guest sigue Q2000 y Q240 commission al 12%; reversals trazables. | Commission contract listo. | Unit presentation+mapper. | Vitest/RTL | agency commission | feature/agency-commission
IMP-WEB-0705 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017 | Group Lifecycle |  | /grupos | Implementar Groups lifecycle | INQUIRY->TENTATIVE->DEFINITE->IN_HOUSE->CLOSED; list/detail; actions válidas. | Invalid jumps no se ofrecen/aplican; property scope; audit ref. | Group contract provisional. | Transition tests + RTL. | Vitest/RTL | src/modules/groups/* | feature/groups-lifecycle
IMP-WEB-0706 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0705, IMP-WEB-0601 | Room Block |  | /grupos/[groupId] | Implementar Room Block | Blocked qty por roomType/date; total; no physical Room delete. | 24 puede ser 16 Deluxe+8 Superior; block separado ATS. | RoomBlock contract listo. | Totals + RTL. | Vitest/RTL | group room-block | feature/group-room-block
IMP-WEB-0707 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups | FEATURE | ALTA | PENDIENTE | IMP-WEB-0706 | Cutoff / Pickup |  | /grupos/[groupId] | Implementar cutoff, release y pickup | Cutoff date/method; release unused; blocked/reserved/available/pickup%. | 24-6=18 retained; pickup 18/24=75%; block available != property ATS. | Contracts listos. | Arithmetic + RTL. | Vitest/RTL | group cutoff/pickup | feature/group-cutoff-pickup
IMP-WEB-0708 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0705, IMP-WEB-0302 | Rooming List |  | /grupos/[groupId]/rooming-list | Implementar Rooming List | Assign GuestProfile to existing Stay IDs; preserve Reservation/Group/Stay IDs. | Occupant change no recrea stay/reservation; capacity validated. | Rooming contract listo. | ID preservation integration. | Vitest/RTL | group rooming list | feature/group-rooming-list
IMP-WEB-0709 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups/folio | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0705, IMP-WEB-0401 | Master Folio |  | /grupos/[groupId] | Integrar Master Folio y routing | Master ref; group charge routing vs individual; Folio public API. | No duplicate charge; personal stays individual; history preserved. | Folio/group contracts listos. | Integration. | Vitest/RTL | group master folio | feature/group-master-folio
IMP-WEB-0710 | S7 B2B & Groups | WEB | Privado | WEB-3 | WEB-4 | groups | FEATURE | ALTA | PENDIENTE | IMP-WEB-0705 | Group Deposits |  | /grupos/[groupId] | Implementar milestones de depósitos | Date/%/amount/status; totals 100%; paid/due/scheduled. | 30/40/30=100%; amount sum base; no auto-capture. | Deposit contract listo. | Arithmetic + RTL. | Vitest/RTL | group deposits | feature/group-deposits
IMP-WEB-0711 | S7 B2B & Groups | WEB | QA | WEB-3 | WEB-4 | b2b-groups | QA | CRÍTICA | PENDIENTE | IMP-WEB-0702, IMP-WEB-0704, IMP-WEB-0707, IMP-WEB-0708, IMP-WEB-0709, IMP-WEB-0710 | V3 — 05 B2B / Groups |  | /empresas /agencias /grupos* | QA B2B/Groups | Actors, rates, commission, lifecycle, block/cutoff/pickup/rooming/master folio/deposits. | Guest price vs commission PASS; IDs preserved; no invalid jumps; finance coherent. | S7 core completo. | Global DoD + scenario regression. | npm run check + manual | S7 | test/b2b-groups-regression
IMP-WEB-0801 | S8 Integrations | WEB | Privado | WEB-3 | WEB-2 | integrations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017 | Integration Center |  | /integraciones | Implementar Integration Center | 7 categorías exactas: Channels, Payments, POS, Fiscal, Locks, Messaging, Accounting; health; property scope. | 7 categorías presentes; counts/health coherentes; no secrets. | Integration list contract listo. | Mapper + RTL + visual. | Vitest/RTL | src/modules/integrations/* | feature/integration-center
IMP-WEB-0802 | S8 Integrations | WEB | Privado | WEB-3 | WEB-2 | integrations | FEATURE | ALTA | PENDIENTE | IMP-WEB-0801 | Booking.com Detail |  | /integraciones/[integrationId] | Implementar detalle/capabilities | Provider/version/health/last sync/capabilities/external refs seguras. | Booking.com capabilities correctas; no credentials secrets; back funciona. | Detail contract listo. | RTL + visual. | Vitest/RTL | integration detail | feature/integration-detail
IMP-WEB-0803 | S8 Integrations | WEB | Privado | WEB-3 | WEB-2 | integrations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0801, IMP-WEB-S301 | Error Queue |  | /integraciones/errores | Implementar Error Queue | Retryable/non-retryable, entity refs, attempts, escalation, filters. | No retry action en non-retryable; counts correctos; no secrets. | Queue contract listo. | Mapper + RTL. | Vitest/RTL | integration error queue | feature/error-queue
IMP-WEB-0804 | S8 Integrations | WEB | Privado | WEB-3 | WEB-2 | integrations | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0803 | Retry/backoff ADR |  | /integraciones/errores | Implementar Retry | Retry solo retryable; scheduled/running/succeeded/exhausted/blocked; anti-double-submit. | No duplicate side effect; attempts/status coherent; failure remains actionable. | Retry contract listo. | Integration retry states. | Vitest/RTL | integration retry | feature/integration-retry
IMP-WEB-0805 | S8 Integrations | WEB | Privado | WEB-3 | WEB-4 | integrations | FEATURE | ALTA | PENDIENTE | IMP-WEB-0802 | Booking.com Mapping |  | /integraciones/[integrationId]/mapping | Implementar mappings | RoomType/RatePlan/Channel external->internal; save; missing mapping error. | BK-DLX etc fixtures coherent; internal IDs selected from allowed catalog. | Mapping contract listo. | Mapper + RTL. | Vitest/RTL | integration mapping | feature/integration-mapping
IMP-WEB-0806 | S8 Integrations | WEB | Privado | WEB-3 | WEB-2 | integrations | FEATURE | ALTA | PENDIENTE | IMP-WEB-0801 | Health Alerts |  | /integraciones | Implementar alertas de salud | Alert id/provider/severity/error ref/action a Error Queue. | Navigation a error correcto; counts update; 0 dead controls. | Alert contract listo. | RTL navigation. | Vitest/RTL | health alerts | feature/integration-health
IMP-WEB-0807 | S8 Integrations | WEB | QA | WEB-3 | WEB-2 | integrations | QA | CRÍTICA | PENDIENTE | IMP-WEB-0802, IMP-WEB-0803, IMP-WEB-0804, IMP-WEB-0805, IMP-WEB-0806 | V3 — 06 Integrations |  | /integraciones* | QA Integrations | Center/detail/queue/retry/mapping/health; idempotency semantics; property scope. | 0 secrets; retry no duplica; mappings safe; navigation/status PASS. | S8 completo. | Global DoD + integration regression. | npm run check + manual | S8 | test/integrations-regression
IMP-WEB-0901 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-3 | permissions | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017 | V3 — 07 Security / Privacy / Access |  | /seguridad/roles | Implementar roles/permissions | Role, permissions, property memberships; hide/disable UI; no asumir backend authorization. | Role modules correctos; property switch no cambia role; permission matrix visible. | Permission contract listo. | Mapper + RTL role cases. | Vitest/RTL | src/modules/permissions/* | feature/roles-permissions
IMP-WEB-0902 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-3 | security | FEATURE | ALTA | PENDIENTE | IMP-WEB-0901 | Sessions / Security |  | /seguridad/sesiones | Implementar sesiones y revocación | List metadata segura; current session; revoke; loading/error. | No token raw; revoke solo success tras response; no PII innecesaria. | Session contract listo. | RTL + security. | Vitest/RTL | security sessions | feature/staff-sessions
IMP-WEB-0903 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-3 | security | FEATURE | ALTA | PENDIENTE | IMP-WEB-0901 | MFA |  | /seguridad/mfa | Implementar MFA UI | Enrollment/status/recovery refs; no persist code/seed; a11y auth. | No codes/seeds en logs/storage; states complete. | MFA contract listo. | RTL + security. | Vitest/RTL | security mfa | feature/mfa
IMP-WEB-0904 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-3 | privacy | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0017 | Privacy Center |  | /seguridad/privacidad | Implementar Consent/Privacy Center | Consent purpose+channel+status+source+timestamp; granular update; DSR entrypoints. | Revocar SMS no revoca Email; no promesa de borrar retenciones legales. | Consent/DSR contract listo. | Mapper + granular RTL. | Vitest/RTL | src/modules/privacy/* | feature/privacy-center
IMP-WEB-0905 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-4 | properties | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0901 | V3 — 09 Multi-property |  | N/A shell | Implementar Property Switcher | Load ACTIVE memberships; authorized only; change scope; Recepción sin global por defecto. | No unauthorized properties; ALL_PROPERTIES solo con permiso; role unchanged. | Membership contract listo. | RTL authorization matrix. | Vitest/RTL | src/modules/properties/*; private shell | feature/property-switcher
IMP-WEB-0906 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-4 | properties | FEATURE | CRÍTICA | PENDIENTE | IMP-WEB-0905 | Multi-property Dashboard |  | /dashboard | Implementar dashboard multi-property | PROPERTY/ALL_PROPERTIES; per-property metrics + consolidated; role aware. | Aggregate after per-property calc; no unauthorized rows; scope visible. | Dashboard contract listo. | Aggregate tests + RTL. | Vitest/RTL | properties dashboard | feature/multi-property-dashboard
IMP-WEB-0907 | S9 Security & Multi-property | WEB | Privado | WEB-2 | WEB-4 | properties/availability | FEATURE | ALTA | PENDIENTE | IMP-WEB-0905, IMP-WEB-0601 | Cross-property Availability |  | /disponibilidad-multi-property | Implementar comparación entre properties | Search dates/roomType; result per authorized property; labels/currency/time. | Only authorized; ATS separado por property; no implicit global. | Cross-property contract listo. | Authorization + result integration. | Vitest/RTL | cross-property availability | feature/cross-property-availability
IMP-WEB-0908 | S9 Security & Multi-property | WEB | Privado | WEB-3 | WEB-2 | reports | FEATURE | ALTA | PENDIENTE | IMP-WEB-0017, IMP-WEB-0905 | V3 — 08 Reporting |  | /reportes | Implementar catálogo/ejecución de reportes | Reports por permission; parameters date/property; result; loading/error/empty. | Only permitted reports; property/date explicit; metrics no calculadas en component. | Report contract listo. | RTL permission + result. | Vitest/RTL | src/modules/reports/* | feature/reports
IMP-WEB-0909 | S9 Security & Multi-property | WEB | Privado | WEB-3 | WEB-2 | reports | FEATURE | MEDIA | PENDIENTE | IMP-WEB-0908 | Reporting export |  | /reportes/[reportId] | Implementar export | Export permission; service; audit/ref if returned; no sensitive client cache. | Unauthorized export absent/blocked; property scope respected. | Export contract listo. | RTL permission. | Vitest/RTL | report export | feature/report-export
IMP-WEB-0910 | S9 Security & Multi-property | WEB | QA | WEB-2 | WEB-3 | security/multiproperty | QA | CRÍTICA | PENDIENTE | IMP-WEB-0902, IMP-WEB-0903, IMP-WEB-0904, IMP-WEB-0906, IMP-WEB-0907, IMP-WEB-0909 | V3 — 07/08/09 |  | /seguridad* /dashboard /reportes* | QA Security/Privacy/Multi-property | Roles/sessions/MFA/consent/scope/dashboard/search/reports/export. | 0 data leaks; ALL_PROPERTIES explícito; no role change; granular consent; no secrets. | S9 completo. | Global DoD + security regression. | npm run check + permission matrix | S9 | test/security-multiproperty-regression
IMP-WEB-1001 | S10 Web Release | WEB | QA | WEB-1 | WEB-2 | e2e | E2E | CRÍTICA | PENDIENTE | IMP-WEB-0113, IMP-WEB-0210, IMP-WEB-0309, IMP-WEB-0409, IMP-WEB-0509, IMP-WEB-0608, IMP-WEB-0711, IMP-WEB-0807, IMP-WEB-0910 | V3 — 12 QA / E2E | 1745:13252 | todas | Instalar Playwright y baseline E2E | Instalar solo ahora; baseURL; smoke public/private; test:e2e script; CI opcional estable. | Playwright no existía antes; smoke PASS; configuración documentada. | Major sprints completos. | E2E smoke PASS. | Playwright | playwright config/tests | test/web-e2e
IMP-WEB-1002 | S10 Web Release | WEB | QA | WEB-1 | WEB-3 | e2e | E2E | CRÍTICA | PENDIENTE | IMP-WEB-1001 | V3 — 12 QA / E2E |  | public | E2E Public Booking + Account | Single/multi-room, optional auth, confirmation, account/history/rewards/promos. | Critical public journeys PASS; failure path básico cubierto. | E2E baseline listo. | Playwright PASS. | Playwright | tests/e2e/public* | test/public-e2e
IMP-WEB-1003 | S10 Web Release | WEB | QA | WEB-3 | WEB-4 | e2e | E2E | CRÍTICA | PENDIENTE | IMP-WEB-1001 | V3 — 12 QA / E2E |  | private | E2E Reservation/Finance/Operations | Cancel/no-show/waitlist/move/extension; folio/payment; discrepancy/OOO-OOS. | Critical private journeys PASS; no false success. | E2E baseline listo. | Playwright PASS. | Playwright | tests/e2e/private* | test/private-e2e
IMP-WEB-1004 | S10 Web Release | WEB | QA | WEB-2 | WEB-4 | e2e | E2E | CRÍTICA | PENDIENTE | IMP-WEB-1001 | V3 — 12 QA / E2E |  | security/multi-property | E2E Security/Multi-property | Role permissions; property switch; unauthorized absence; consent channels; report export. | 0 leak; ALL_PROPERTIES explicit; journeys PASS. | E2E baseline listo. | Playwright PASS. | Playwright | tests/e2e/security* | test/security-e2e
IMP-WEB-1005 | S10 Web Release | WEB | QA | WEB-2 | WEB-1 | accessibility | QA | CRÍTICA | PENDIENTE | IMP-WEB-1002, IMP-WEB-1003, IMP-WEB-1004 | Final regression | 1745:13252 | todas | Auditoría final accesibilidad | Keyboard/focus/labels/contrast/target >=24x24/auth paste/autocomplete/errors. | 0 defectos críticos/altos; journeys críticos por teclado. | E2E PASS. | A11y audit PASS. | manual/tooling | whole web | test/a11y-final
IMP-WEB-1006 | S10 Web Release | WEB | QA | WEB-4 | WEB-1 | release | QA | CRÍTICA | PENDIENTE | IMP-WEB-1005 | Final regression | 1745:13252 | todas | Regresión final Web | npm run check + e2e + routes + roles/sidebar + no legacy/V1 + no dead controls + docs. | 0 critical/high; all checks PASS; architecture clean; release candidate. | All Web tasks done. | Release DoD PASS. | npm run check + test:e2e + manual | whole web | release/web-rc
IMP-AND-0001 | S0 Android Foundation | ANDROID | Infra | ANDROID-1 | WEB-2 | android-foundation | DOC | CRÍTICA | READY |  | Implementation Ready — Android V2 + V3 | 238:132 | N/A | Confirmar stack Android | Validar con docente lenguaje/UI toolkit/min SDK/Gradle/arquitectura; registrar DEC antes de proyecto. | Stack aprobado/documentado; no asumir Compose/XML/Kotlin/Java sin confirmación. | Requisito docente disponible. | Review documental PASS. | manual | docs Android + ADR | chore/android-sprint-0
IMP-AND-0002 | S0 Android Foundation | ANDROID | Infra | ANDROID-1 | WEB-2 | android-foundation | INFRA | CRÍTICA | PENDIENTE | IMP-AND-0001 | Android architecture docs | 238:132 | N/A | Inicializar proyecto Android | Crear dentro frontend/pms-hotel-android; no git init; conservar docs; build mínimo. | Proyecto compila; un solo .git; no feature screens. | 0001 COMPLETADA. | Build PASS. | Gradle build/assemble | project files | chore/android-sprint-0
IMP-AND-0003 | S0 Android Foundation | ANDROID | Design System | ANDROID-1 | WEB-1 | android-theme | INFRA | ALTA | PENDIENTE | IMP-AND-0002 | Android Final | 238:132 | N/A | Crear theme/tokens Android | Mapear tokens Figma al mecanismo Android; no inventar dark mode. | Theme refleja Figma; semantic tokens; no random hardcodes. | Proyecto buildable. | Visual smoke + build. | build | theme resources | chore/android-sprint-0
IMP-AND-0004 | S0 Android Foundation | ANDROID | Arquitectura | ANDROID-1 | WEB-3 | android-layers | INFRA | CRÍTICA | PENDIENTE | IMP-AND-0002 | Android layered flow |  | N/A | Crear capas Remote->DTO->Mapper->Domain->UI/State | Packages base; sample técnico mínimo si requiere compilar; no business modules masivos. | Direction clara; UI no hace network directo ni consume DTO. | Stack aprobado. | Architecture review + build. | build | layer folders | chore/android-sprint-0
IMP-AND-0005 | S0 Android Foundation | ANDROID | Infra | ANDROID-1 | WEB-4 | remote | INFRA | CRÍTICA | PENDIENTE | IMP-AND-0004 | Android remote layer |  | N/A | Configurar cliente remoto | Base URL/env; transport errors; no endpoints business; no secrets. | Remote reusable; no hardcoded token; errors tipados. | 0004 COMPLETADA. | Unit transport test. | unit/build | remote client | chore/android-sprint-0
IMP-AND-0006 | S0 Android Foundation | ANDROID | Testing | ANDROID-1 | WEB-3 | testing | INFRA | CRÍTICA | PENDIENTE | IMP-AND-0002 | Android testing docs |  | N/A | Configurar tests baseline | Unit mapper/state + UI test capability según stack. | Test command PASS con smoke tests. | Project buildable. | Tests PASS. | unit/ui smoke | test config | chore/android-sprint-0
IMP-AND-0007 | S0 Android Foundation | ANDROID | Navigation | ANDROID-1 | WEB-2 | navigation | INFRA | ALTA | PENDIENTE | IMP-AND-0002, IMP-AND-0003 | Android final flows | 238:132 | N/A | Configurar navegación técnica | Destinations Stay/Account/Loyalty/States sin screens finales; back stack policy. | Navigation compila; 0 business logic placeholder. | Stack/navigation approved. | Navigation smoke. | ui smoke | navigation foundation | chore/android-sprint-0
IMP-AND-0008 | S0 Android Foundation | ANDROID | Mocks/State | ANDROID-1 | WEB-3 | mocks-state | INFRA | ALTA | PENDIENTE | IMP-AND-0004, IMP-AND-0005 | Android offline/state docs |  | N/A | Configurar mock remote + state pattern | Mocks DTO remote success/null/empty/error/offline; state holder Loading/Success/Empty/Error/Offline. | UI futura puede cambiar mock por real sin tocar Domain; offline explicit. | Remote layers ready. | Unit tests. | unit | mock/state base | chore/android-sprint-0
IMP-AND-0009 | S0 Android Foundation | ANDROID | QA | ANDROID-1 | WEB-2 | foundation | QA | CRÍTICA | PENDIENTE | IMP-AND-0002, IMP-AND-0003, IMP-AND-0004, IMP-AND-0005, IMP-AND-0006, IMP-AND-0007, IMP-AND-0008 | Android foundation | 238:132 | N/A | Cerrar Sprint 0 Android | Build/tests/navigation/theme/remote/mock/layers/docs; 0 feature final. | All checks PASS; no DTO UI; no secrets; ready features. | Dependencies complete. | Android Global DoD. | build + tests | Android foundation | chore/android-sprint-0
IMP-AND-0101 | S1 Android Stay & Services | ANDROID | Estancia | ANDROID-1 | WEB-3 | stay | FEATURE | CRÍTICA | PENDIENTE | IMP-AND-0009 | Android 01 Estancia y servicios | 238:132 | Stay Home | Crear Stay contracts | ReservationStay/room/dates/status DTO->Domain; mock remote. | Reservation != Stay; mapper tests; UI-ready Domain. | S0 Android complete. | Unit mapper/service. | unit | stay layers | feature/android-stay-contract
IMP-AND-0102 | S1 Android Stay & Services | ANDROID | Estancia | ANDROID-1 | WEB-3 | stay | FEATURE | CRÍTICA | PENDIENTE | IMP-AND-0101 | Android 01 Estancia y servicios | 238:132 | Stay Home | Implementar pantalla Estancia | Room/type/dates/status/actions; loading/error/offline; Figma. | No DTO UI; navigation a services; offline explicit. | 0101 COMPLETADA. | UI + visual. | unit/ui | stay screen | feature/android-stay-home
IMP-AND-0103 | S1 Android Stay & Services | ANDROID | Servicios | ANDROID-1 | WEB-3 | services | FEATURE | ALTA | PENDIENTE | IMP-AND-0102 | Android 01 Estancia y servicios | 238:132 | Services | Implementar servicios y solicitud | Catalog DTO->Domain; detail/request; submitting/success/error/offline. | Only services current stay/property; no false success/double submit. | Service contract ready. | Mapper + UI. | unit/ui | services module | feature/android-services
IMP-AND-0104 | S1 Android Stay & Services | ANDROID | Chat | ANDROID-1 | WEB-3 | messaging | FEATURE | ALTA | PENDIENTE | IMP-AND-0102 | Android 01 Estancia y servicios | 238:132 | Chat | Implementar chat con Recepción | Thread/messages; send to Reception only; offline/error. | No direct HK/Maintenance recipient; no PII logs. | Messaging contract reviewed. | Mapper + UI send/offline. | unit/ui | messaging | feature/android-chat
IMP-AND-0105 | S1 Android Stay & Services | ANDROID | Valet | ANDROID-1 | WEB-3 | valet | FEATURE | MEDIA | PENDIENTE | IMP-AND-0102 | Android 01 Estancia y servicios | 238:132 | Valet | Implementar Valet/Parking | Status/request/pickup según Figma; remote mock; offline/error. | No financial assumptions fuera Figma; linked to stay/property. | Valet contract confirmed. | UI tests. | unit/ui | valet | feature/android-valet
IMP-AND-0106 | S1 Android Stay & Services | ANDROID | QA | ANDROID-1 | WEB-3 | stay-services | QA | CRÍTICA | PENDIENTE | IMP-AND-0102, IMP-AND-0103, IMP-AND-0104, IMP-AND-0105 | Android 01 Estancia y servicios | 238:132 | Stay/Services | QA Estancia/Servicios | Stay/services/chat/valet/loading/error/offline/navigation. | All flows PASS; Reception boundary; Figma parity. | S1 tasks done. | Android Global DoD. | build/tests/manual | Android S1 | test/android-stay-services
IMP-AND-0201 | S2 Android Account | ANDROID | Cuenta | ANDROID-1 | WEB-2 | account | FEATURE | CRÍTICA | PENDIENTE | IMP-AND-0009 | Android 02 Cuenta, checkout y factura | 238:132 | Account | Crear Account/Profile contracts | GuestAccount/Profile separados; remote->DTO->Mapper->Domain. | No Staff auth; no provider JSON UI; mapper tests. | S0 complete. | Unit. | unit | account layers | feature/android-account-contract
IMP-AND-0202 | S2 Android Account | ANDROID | Cuenta | ANDROID-1 | WEB-2 | account | FEATURE | ALTA | PENDIENTE | IMP-AND-0201 | Android 02 Cuenta, checkout y factura | 238:132 | Account/Profile | Implementar cuenta/perfil | Display/edit Profile; loading/error/offline; submit. | Account/Profile separation; no secrets; save states correct. | 0201 complete. | UI tests. | unit/ui | account/profile screens | feature/android-account-profile
IMP-AND-0203 | S2 Android Account | ANDROID | Checkout/Factura | ANDROID-1 | WEB-4 | checkout | FEATURE | CRÍTICA | PENDIENTE | IMP-AND-0102 | Android 02 Cuenta, checkout y factura | 238:132 | Checkout/Invoice | Implementar checkout e invoice | Charges/balance/status Folio read model; invoice ref/status/date/total; offline/error. | Finance no recalculated in UI; no sensitive file persisted; no provider raw data. | Folio/Fiscal mobile contract reviewed. | Mapper + UI/security. | unit/ui | checkout/invoice | feature/android-checkout-invoice
IMP-AND-0204 | S2 Android Account | ANDROID | QA | ANDROID-1 | WEB-2 | account-checkout | QA | CRÍTICA | PENDIENTE | IMP-AND-0202, IMP-AND-0203 | Android 02 Cuenta, checkout y factura | 238:132 | Account/Checkout | QA Cuenta/Checkout/Factura | Profile/checkout/invoice/states/navigation/contracts. | Guest/Staff separation; finance coherent; Figma parity. | S2 done. | Android Global DoD. | build/tests/manual | Android S2 | test/android-account-checkout
IMP-AND-0301 | S3 Android Loyalty | ANDROID | Loyalty | ANDROID-1 | WEB-2 | rewards | FEATURE | ALTA | PENDIENTE | IMP-AND-0009 | Android 03 Loyalty, promociones y perfil | 238:132 | Rewards | Implementar Rewards | Ledger/balance Domain cross-app; offline/error/empty. | CANCELLED/NO_SHOW no elegibles; ledger read-only. | Reward contract reviewed. | Mapper + UI. | unit/ui | rewards | feature/android-rewards
IMP-AND-0302 | S3 Android Loyalty | ANDROID | Promociones | ANDROID-1 | WEB-2 | promotions | FEATURE | ALTA | PENDIENTE | IMP-AND-0009 | Android 03 Loyalty, promociones y perfil | 238:132 | Promotions | Implementar Promotions | Eligibility/vigencia/stacking reason; states. | Incompatible no combinable; reasons correct. | Promotion contract reviewed. | Mapper + UI. | unit/ui | promotions | feature/android-promotions
IMP-AND-0303 | S3 Android Loyalty | ANDROID | Perfil | ANDROID-1 | WEB-2 | profile | FEATURE | ALTA | PENDIENTE | IMP-AND-0201 | Android 03 Loyalty, promociones y perfil | 238:132 | Profile | Implementar perfil final | Figma layout/edit/states; reuse Account/Profile Domain. | No duplicated model; PII safe; save states correct. | Profile contract ready. | UI tests. | unit/ui | profile | feature/android-profile
IMP-AND-0304 | S3 Android Loyalty | ANDROID | QA | ANDROID-1 | WEB-2 | loyalty-profile | QA | CRÍTICA | PENDIENTE | IMP-AND-0301, IMP-AND-0302, IMP-AND-0303 | Android 03 Loyalty, promociones y perfil | 238:132 | Rewards/Promos/Profile | QA Loyalty/Profile | Rewards/promotions/profile/offline/error/empty/navigation. | Cross-app semantics PASS; Figma parity; no DTO UI. | S3 done. | Android Global DoD. | build/tests/manual | Android S3 | test/android-loyalty
IMP-AND-0401 | S4 Android Release | ANDROID | Estados | ANDROID-1 | WEB-2 | ui-states | SHARED | CRÍTICA | PENDIENTE | IMP-AND-0009 | Android 04 Loading, error y offline | 238:132 | Universal States | Implementar Loading/Error/Empty/Offline shared | Reusable state UI; retry callback; accessible; no business logic. | Features reutilizan states; offline explicit; retry actionable. | Figma states reviewed. | UI tests. | ui | shared state UI | feature/android-universal-states
IMP-AND-0402 | S4 Android Release | ANDROID | Estados | ANDROID-1 | WEB-3 | offline | FEATURE | CRÍTICA | PENDIENTE | IMP-AND-0401, IMP-AND-0106, IMP-AND-0204, IMP-AND-0304 | Android 04 Loading, error y offline | 238:132 | All | Integrar states universales | Reemplazar estados ad-hoc; retry; stale indication donde aplica. | 0 remote screen sin Loading/Error; Offline según Figma; no false success. | Feature screens done. | Regression states. | ui/manual | all Android | feature/android-state-integration
IMP-AND-0403 | S4 Android Release | ANDROID | QA | ANDROID-1 | WEB-2 | accessibility | QA | CRÍTICA | PENDIENTE | IMP-AND-0402 | Android final regression | 238:132 | All | Auditoría accesibilidad Android | TalkBack/labels/targets/contrast/focus/auth/errors. | 0 critical/high accessibility defects; primary journeys operable. | Features done. | A11y PASS. | manual/tooling | whole Android | test/android-a11y
IMP-AND-0404 | S4 Android Release | ANDROID | QA | ANDROID-1 | WEB-3 | release | QA | CRÍTICA | PENDIENTE | IMP-AND-0403 | Android final regression | 238:132 | All | Regresión final Android | Build/tests/navigation/states/contracts/no DTO UI/no secrets. | 0 critical/high; all checks PASS; release candidate. | All Android tasks done. | Release DoD PASS. | build/tests/manual | whole Android | release/android-rc

## 02_Owners
Owner | Aplicación | Responsabilidad primaria | Módulos principales | Dependencias / coordinación | Reviewer habitual | Reglas especiales
WEB-1 | WEB | Booking público / Multi-room / Checkout | booking; checkout; rooms UI pública; shared usado por booking | Consume Availability/Payments de WEB-4; Auth de WEB-2; Reservation creation de WEB-3 | WEB-2 | No modifica core Availability, Auth o Payments sin reviewer del owner correspondiente.
WEB-2 | WEB | Identity / Account / Rewards / Security / Privacy / Multi-property | auth; account; profile; rewards; promotions; privacy; permissions; security; properties | Reservation history con WEB-3; revenue metrics multi-property con WEB-4 | WEB-3 | Guest/Staff separados; Property scope no cambia role; no ALL_PROPERTIES implícito.
WEB-3 | WEB | Reservations / Operations / B2B / Groups / Integrations / Reporting UI | reservations; stays; housekeeping; maintenance; companies; agencies; groups; integrations; reports; concierge | Availability/Folio/Payments con WEB-4; permissions con WEB-2 | WEB-4 | No crea side effects financieros/inventario sin contrato del owner correspondiente.
WEB-4 | WEB | Folio / Payments / Availability / Rates / Inventory / Revenue / Channels | folio; payments; receivables; availability; rates; inventory; revenue; channels | Public booking consume sus APIs; Reservations/Groups disparan impactos dependientes | WEB-1 | No PAN/CVV; Physical Inventory != Availability; historial financiero append-only.
ANDROID-1 | ANDROID | Aplicación Android completa | stay; services; messaging; valet; account; checkout; invoice; rewards; promotions; profile; offline states | Contratos cross-app con WEB-2/3/4 según dominio | Reviewer Web del dominio afectado | No inventa statuses/contracts incompatibles; UI no consume DTO crudo.

## 03_Workflow_DoR_DoD
Sección | Elemento | Regla obligatoria | Evidencia mínima
Workflow | PENDIENTE | Tarea documentada pero no habilitada. No se programa. | Backlog sin rama/PR.
Workflow | READY | Todas las dependencias están COMPLETADAS y cumple DoR. El owner puede tomarla. | Dependencias verificadas + DoR PASS.
Workflow | EN_PROGRESO | Owner trabajando en rama dedicada. No compartir el mismo archivo con otro owner sin coordinación. | Rama + fecha inicio.
Workflow | EN_QA | Implementación terminada por owner; reviewer ejecuta aceptación y DoD. Owner no puede autoaprobar una tarea cross-domain/shared. | PR + checks + evidencia.
Workflow | BLOQUEADA | Existe dependencia, contrato, decisión o acceso faltante que impide continuar sin inventar. | Observación con causa y owner del bloqueo.
Workflow | COMPLETADA | Criterios de aceptación + DoD específico + Global DoD PASS y reviewer aprueba. | PR/commit + tests + capturas/logs aplicables.
Transición | PENDIENTE → READY | Solo si todas las dependencias están COMPLETADAS y DoR está completo. | Revisión del owner/reviewer.
Transición | READY → EN_PROGRESO | Owner crea/usa rama sugerida y registra inicio. | Rama + fecha.
Transición | EN_PROGRESO → EN_QA | Owner ejecutó pruebas propias y considera aceptación completa. | PR abierto + checks locales.
Transición | EN_QA → EN_PROGRESO | Si falla cualquier aceptación o DoD, NO se completa; vuelve a desarrollo. | Comentario reviewer con fallo reproducible.
Transición | EN_QA → COMPLETADA | Solo con aceptación y DoD PASS. | Reviewer + evidencia.
DoR Web | Fuente | Figma/requisito/documentación exacta identificada. Infra puede usar Ruta: N/A — infraestructura. | Sección Figma/ADR registrada.
DoR Web | Owner | Owner y reviewer definidos; si cruza dominios, reviewer debe ser el owner afectado. | Owner/Reviewer llenos.
DoR Web | Dependencias | Todas las dependencias del backlog están COMPLETADAS. | IDs verificados.
DoR Web | Contrato | DTO/API real o PROVISIONAL claramente identificado si hay red. | Contract doc o nota provisional.
DoR Web | Scope | Role/permission/property scope definidos cuando aplique. | Regla/fixture identificados.
DoR Web | Estados | Loading/Error/Empty/Offline/Submitting identificados cuando apliquen. | Acceptance incluye estados.
Global DoD Web | Arquitectura | UI no hace fetch; UI no consume DTO; Service retorna DTO; Mapper puro; Domain limpio; boundaries PASS. | lint/typecheck + review.
Global DoD Web | Calidad | npm run lint, typecheck, test y build PASS. En release también E2E. | Logs/checks.
Global DoD Web | UI | Figma consistente; 0 clipping; 0 overlaps no intencionales; 0 controles visibles muertos; responsive donde aplique. | Captura/video/manual QA.
Global DoD Web | Navegación | Rutas válidas; Back/Continue/Confirm correctos; no container click accidental; no V1/legacy. | Journey manual/E2E.
Global DoD Web | Datos | Fixtures coherentes; IDs del mismo escenario; cálculos correctos; Reservation != Stay; Property scope correcto. | Tests + fixture refs.
Global DoD Web | Seguridad | No secrets/PII logs; no PAN/CVV; Guest/Staff separados; permisos y scope representados correctamente. | Security review.
Global DoD Web | Accesibilidad | Keyboard, focus, labels, contraste, target >=24x24, auth paste/autocomplete, error no solo color. | A11y review.
DoR Android | Stack | Stack Android aprobado/documentado antes de crear arquitectura dependiente. | DEC Android.
DoR Android | Contrato | Contrato cross-app identificado; no inventar status/API incompatible. | Referencia cross-app.
Global DoD Android | Arquitectura | Remote→DTO→Mapper→Domain→State/UI; UI no consume DTO ni hace red directa. | Code review/tests.
Global DoD Android | Calidad | Build/compile + unit/UI tests PASS. | Logs.
Global DoD Android | UI/Estados | Figma parity; navegación/back; Loading/Error/Empty/Offline; no false success. | UI tests/manual.
Global DoD Android | Seguridad/A11y | No secrets/PII; Guest/Staff semantics; TalkBack/labels/targets/contrast/focus. | Review.
PR | Shared | Cambios a shared requieren reviewer adicional y evidencia de reutilización real. | PR reviewer.
PR | Cross-domain | Si la tarea afecta otro owner, ese owner debe revisar antes de completar. | Reviewer correspondiente.
Regla | No saltar tareas | No comenzar una tarea dependiente si su dependencia no está COMPLETADA, salvo cambio explícito aprobado en backlog. | Backlog actualizado.

## 04_Figma_Map
Aplicación | Bloque Figma / Fuente | Node ID | Owner | Módulo(s) | Ruta(s) principal(es) | Notas
WEB | High Fidelity — Web Pública / Final V3 | 17:2 | WEB-1 / WEB-2 | booking, auth, account, checkout, rooms | /, /habitaciones, /reserva, /acceso, /cuenta | Public 01-05.
WEB | V3 — 01 Reservation Engine |  | WEB-3 | reservations, stays, calendar | /reservas, /calendario | Reservation detail y Calendar se trazan por nombre de sección/pantalla; Node ID no verificado.
WEB | V3 — 02 Folio & Payments |  | WEB-4 | folio, payments, receivables | /folios/*, /pagos | Advanced Folio canonical.
WEB | V3 — 03 Operations |  | WEB-3 | housekeeping, maintenance, concierge | /housekeeping, /mantenimiento, /conserjeria | Discrepancies y overlays se trazan por nombre de flujo; Node IDs no verificados.
WEB | V3 — 04 Commercial / Availability / Revenue |  | WEB-4 | availability, rates, inventory, revenue, channels | /availability, /revenue* | Physical inventory != sellable availability.
WEB | V3 — 05 B2B / Groups |  | WEB-3 | companies, agencies, groups | /empresas, /agencias, /grupos | Agency Commission y Group Lifecycle se trazan por nombre de ADR/flujo; Node IDs no verificados.
WEB | Room Block / Cutoff / Pickup / Rooming / Master Folio |  | WEB-3 + WEB-4 review | groups, folio | /grupos/[groupId]* | Finance-impact tasks require WEB-4 review.
WEB | V3 — 06 Integrations |  | WEB-3 | integrations | /integraciones* | Integration Detail, Error Queue, Mapping y Health se trazan por nombre de pantalla/flujo; Node IDs no verificados.
WEB | V3 — 07 Security / Privacy / Access |  | WEB-2 | security, privacy, permissions | /seguridad* | Privacy Center canonical.
WEB | V3 — 08 Reporting |  | WEB-3 | reports | /reportes* | Metrics must declare property/date scope.
WEB | V3 — 09 Multi-property |  | WEB-2 + WEB-4 review | properties | /dashboard, /disponibilidad-multi-property | ALL_PROPERTIES = authorized set only.
WEB | V3 — 12 QA / E2E | 1745:13252 | Todos | qa/e2e | todas | Final regression reference.
ANDROID | Implementation Ready — Android V2 + V3 | 238:132 | ANDROID-1 | stay, services, account, checkout, rewards, states | Android navigation | Cross-app reviewers depend on domain.
Política de Node IDs
Regla | Solo se registran Node IDs verificados de forma independiente. Una celda vacía NO autoriza inventar un ID; usar nombre de sección/pantalla.
Verificados | 17:2 (Web Pública final); 238:132 (Android Implementation Ready); 1745:13252 (regresión final). 550:294 y 31:132 quedan disponibles como referencias conocidas cuando una tarea corresponda exactamente.

## 05_Consistency_Audit
Tipo | Elemento | Corrección aplicada | Resultado
Ubicación | Backlog maestro | Ubicación canónica definida como docs/Backlog_Implementacion_PMS_V1.xlsx. | CORREGIDO
Referencia | IMP-WEB-0004 | Fuente exacta -> frontend/pms-hotel-web/docs/31_DESIGN_TOKEN_FOUNDATION.md. | CORREGIDO
Referencia | IMP-WEB-0006..0011 | Todas las referencias docs/ ambiguas se sustituyeron por rutas completas de repositorio. | CORREGIDO
Documento | 04_MODULE_BOUNDARIES.md | Se incorpora como especificación autoritativa de imports/ESLint boundaries. | CORREGIDO
Dependencia | IMP-WEB-0016 | Ahora depende de IMP-WEB-0001..0015 para documentar la implementación real completa. | CORREGIDO
Figma | Node IDs no verificados | Eliminados del backlog/Figma Map. Celdas vacías obligan a usar el nombre de sección, nunca inventar un ID. | CORREGIDO
Figma | Node IDs verificados | Se conservan únicamente referencias verificadas aplicables: 17:2, 238:132, 1745:13252; 550:294 y 31:132 solo cuando correspondan exactamente. | CORREGIDO
Mocks | IDs runtime | Documentación corregida para usar IDs de negocio coherentes; Figma Node IDs nunca son runtime IDs. | DOC PATCH
State | TanStack Query | Documentación corregida: decisión ya aprobada; deja de decir 'elegir en Sprint 0'. | DOC PATCH
Testing | Playwright | Documentación corregida: diferido hasta IMP-WEB-1001, no Sprint 0. | DOC PATCH
DoR | Ruta infraestructura | Documentación corregida: Route: N/A — infraestructura es válido para tareas puramente técnicas. | DOC PATCH
Git | Sprint 0 | Documentación corregida: excepción aprobada para un PR cohesivo IMP-WEB-0001..0017 en chore/web-sprint-0. | DOC PATCH
Manifest | MANIFEST.json | Debe eliminarse del repo: era inventario estático pre-Codex y quedó obsoleto al añadir nuevos archivos. | ELIMINAR